## Project Overview
Development Document Template
Project Name:
EOP Pallet Return Dashboard
Link to External BRD
EOP Pallet Return Dashboard Scope & Deliverable:
The EOP Pallet Return Dashboard ideated as a follow up from the pallet simulation model. Stakeholders wanted a way to track actual pallet returns from the pallet return program versus the simulated output from the pallet simulation model. The majority of scope included building a dashboard that allowed users to see actual pallet return down to location level with different views. One further piece of scope included developing a metric to estimate the total number of turns each pallet was recognizing through the NA MSC network.

## Timeline
Project Timeline
Start Date: | 2024-08-28 | End Date: | 2024-08-28 | Est. Effort: | 1 | Total Effort: | 0
|  |  |  | Est. Weeks: | 0.2
Phase/Item | [5 empty] | Est. Start Date | Est. End Date | Est. Effort | Act. Start Date | Act. End Date | Act. Effort | Status
Phase 1: Project Scope, Charter & Wireframe Development
1.1 Project Charter Development | [5 empty] | 2024-08-28 | 2024-08-28 | 1 |  |  | 0
1.2 Scoping Meeting and Stakeholder alignment | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
1.3 Wireframe Development & Sign off | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Phase 2: Data Discovery & Clean-up
2.1 Data requirement identification | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
2.2 Data gathering | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
2.3 EDA & Data Clean-up | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Phase 3: Back-end Development
3.1 Script Development | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
3.2 Debugging | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
3.3 …. | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Phase 4: Front-End Development
4.1 Layout development | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
4.2 Data connections | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
4.3 Testing | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Phase 5: UAT
5.1 Stakeholder UAT Kick off | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
5.2 Feedback implementation | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
5.3 …. | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Phase 6: Release
6.1 Automation & Scheduling | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
6.2 Documentation Finalization | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
6.3 Hand-off or release | [5 empty] | 2024-08-29 | 2024-08-28 | 0 |  |  | 0
Formulas:
Est. Start Date = WORKDAY([Est. End Date, row above],1)
Est. End Date = WORKDAY([Est. Start Date],([Est. Effort]-1))
Act. Effort = NETWORKDAYS([Act. Start Date],[Act. End Date])

## Wireframe
Wireframe:

## Sheet1 (hidden)
STATUs | Assumptions
Completed | Risk
Delayed | Aligned
Blocked | Needs Discussion
In Progress
Not Started

## Data and Assumptions
Assumptions/Risks: |  |  |  |  | Data:
Item | Status? | Group | Accountable | Description | Inputs: Outbound Pallet Data - Plants Dashboard & Simulation |  |  |  |  | Output: Dashaboard/Tool Tables Created
Naperville Truck Capacity | Aligned | Data Ingestion | Chris Blanche | Naperville is capped at 60 pallets per truck. If pallets are <60, use actual number. | Item | Source | Table Name | Columns | Description | Item | Location | File Creation Process Location (Workflow/Script) | Table Name | Description
All other Truck Capacity | Aligned | Data Ingestion | Chris Blanche | All other location capacities are capped at 30 pallets per truck. If actual pallets > 30, use 30 else use actual number. | 1 | SAP -BW | EKKO | LIFNR: ORIG_KEY | IBL of origin location in pallet transactions | 1 | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\SAP Data | https://alteryx.mdlz.com/gallery/#!/app/vfr_sto_3-6_with_POS_filter/66a016d8bf5766a342d0edb8 | *_Outbound_Pallets.csv | Provides actual pallet outbound information for upstream locations including Richmond, Naperville, Portland, Chicago & Salinas. * signifies branch name. There is one file for each US bakery location and Salinas respectively.
Richmond Excluded SKUs | Aligned | Data Ingestion | Chris Blanche | Three skus are excluded from data ingestion specifically for the Richmond Bakery: #2734 Regular Nilla ; #7713 Family Size Nilla ; #0057 Premiums | 2 | SAP -BW | EKPO | BERID: DEST_KEY | IBL of destination location in pallet transactions
Portland IBLs | Aligned | Data Ingestion | Chris Blanche | Ingest data from Portland FC IBL- 1143, exclude data from Portland Bakery IBL - 6200 | 3 | SAP -BW | LIPS | VBELN: Delivery Document | Delivery number for a picked order
Simulation Timing | Aligned | Pallet Simulation | Robby Waite | Simulation is run on a weekly basis. All inputs are aggregated on a weekly level. | 4 | SAP -BW | LIKP | WADAT_IST: Delivery Date | Actual goods movement date
Mondelez Block Pallet Injeciton | Aligned | Pallet Simulation | Robby Waite | Mondelez Block pallets are only injected in Salinas, MX. | 5 | SAP -BW | LIPS | LFIMG: Picked Cases | Filled case quantity on an order. Used to calculated total pallets on an order
Pallet Loss Rate | Aligned | Pallet Simulation | Chris Blanche | Pallets are lost at a fixed rate of 6% per turn. | 6 | SAP -BW | MARM | PAL_UMREZ: Picked Pallets | Total calculated pallets based on actual case quantity
Pallet Damage Rate | Aligned | Pallet Simulation | Chris Blanche | Pallets are damaged dynamically based on the turn cycle: Turn 1: 4% Turn 2: 8% Turn 3: 16%
Truck Capacity | Aligned | Pallet Simulation | Chris Blanche | Trucks can fit a maximum of 540 pallets. | Inputs: Location Mapping Dashboard |  |  |  |  | Output: Dashaboard/Tool Tables Created
Pallet Return Locations | Aligned | Pallet Simulation | Chris Blanche | Pallets can only be returned to these bakeries: Richmond, Naperville, Chicago, Portland | Item | Source | Table Name | Columns | Description | Item | Location | File Creation Process Location (Workflow/Script) | Table Name | Description
Pallet Surplus | Aligned | Pallet Simulation | Chris Blanche | Any pallets left in the network after weekly pallet demand is covered in the pallet return locations is considered surplus. | 1 | Excel - Manual File | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Simulation\Location Map.xlsx | Area Region Plant Type IBL IBL Description | Area for branch location Region associated w/ plant Type of plant (DSD, RDC, etc.) Plant IBL number Plant name | 1 | Same as input | N/A | Same as input | Same as input
Pallet Turns | Aligned | Pallet Simulation | Chris Blanche | Pallets can be returned upstream a maximum of 3 times before they die.
Pallet Shipment Timeline | Aligned | Data Ingestion | Chris Blanche | Chicago started to ship on Mondelez pallets from 07/15/2024; all other locations started on 3/1/2024 | Inputs: Outbound Pallets - 3PL Dashboard |  |  |  |  | Output: Dashaboard/Tool Tables Created
[5 empty] | Item | Source | Table Name | Columns | Description | Item | Location | File Creation Process Location (Workflow/Script) | Table Name | Description
[5 empty] | 1 | 3PL Email Distribution | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\3PL Data\3PL_Outbound_Pallets.csv | Date Delivery Number Ship From Ship To Mdlz Pallet Count | Date associated with DN Delivery number for picked order IBL order sending location IBL of order receiving location Total number of block pallets on the order | 1 | Same as input | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Workflows and Macros\3pl_Outbound_Pallets.yxmd | Same as input | Same as input
[5 empty] | 2 | 3PL Email Distribution | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\3PL Data\3PL_Customer_Shipments.csv | Date Delivery Number Ship From Ship To Customer Mdlz Pallet Count | Date associated with DN Delivery number for picked order IBL order sending location IBL of order receiving location Total number of block pallets on the order | 2 | Same as input | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Workflows and Macros\3pl_Outbound_Pallets.yxmd | Same as input | Same as input
[5 empty] | Inputs: Turns Data Simulation |  |  |  |  | Output: Dashaboard/Tool Tables Created
[5 empty] | Item | Source | Script Location / Output File | Columns | Description | Item | Location | File Creation Process Location (Workflow/Script) | Table Name | Description
[5 empty] | 1 | Pallet Simulation | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Code\turns_metric.ipynb | weekly_demand expected_pallet_return expected_pallet_surplus year week | total weekly demand for US bakeries Expected pallet returns to US bakeries Expected excess pallets after return Year Week of year | 1 | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Simulation\turns_data.csv | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Code\turns_metric.ipynb | turns_data.csv | Pallet simulation output providing daily values for expected pallet return and expected pallet surplus for the entire network. Check bottom of script if output is not updating. Some outputs can be commented out.
[5 empty] | 2 | Pallet Simulation | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Code\turns_metric.ipynb | Location week Expected Pallet Return | Name of branch location Week of year Expected pallet return for respective week | 2 | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Simulation\returns_by_location.csv | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Code\turns_metric.ipynb | returns_by_location.csv | Pallet simulation output providing daily values for expected pallet return and expected pallet surplus by location. Check bottom of script if output is not updating. Some outputs can be commented out.
[5 empty] | Inputs: Pallet Return Data Dashboard |  |  |  |  | Output: Dashaboard/Tool Tables Created
[5 empty] | Item | Source | Table Name | Columns | Description | Item | Location | File Creation Process Location (Workflow/Script) | Table Name | Description
[5 empty] | 1 | SAP-BW | EKPO | PO Number Material Number Material Description | PO number of order SKU item number SKU item description | 1 | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\SAP Data\Pallet_Return_Data.csv | \\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Workflows and Macros\Pallet_Return_Workflow.yxmd | Pallet_Return_Data.csv | Actual pallet returns from DSD plants back upstream. Each row represents the amount of pallets returned on a single PO.
[5 empty] | 2 | SAP-BW | LIPS | Ship From Quantity Delivery Number | IBL of order shipping location Number of pallets sent on each order Delivery number of each order
[5 empty] | 3 | SAP-BW | LIKP | Delivery Date Ship To | Actual date of order delivery IBL of order receiving location
[10 empty] | Output: Dashaboard/Tool Tables Created (Manually within Dashboard based on above tables) |  | File Creation Process Location (Workflow/Script) | Table Name | Description
[10 empty] | 1 | Dashboard | Power BI Power Query | Dim_BranchMap | A copy of location map used only for Pallet Return data to pull Return From Location Names (To differentiate with Return To which links to Dim_LocationMap)
[10 empty] | 2 | Dashboard | Power BI Power Query | DSD_WeeklyReceive_Consolidated | Main table for DSD page to calculate return % - Consolidated weekly receive from Plants and RDC, then merged with DSD_Weekly_Return_Actual
[10 empty] | 3 | Dashboard | Power BI Dax Query | 3PL_WeeklyOutbound | Summarize 3PL outbound pallets by week and ship from
[10 empty] | 4 | Dashboard | Power BI Dax Query | Dim_DateTable | Dimension table for daily calendar
[10 empty] | 5 | Dashboard | Power BI Dax Query | Dim_WeekTable | Dimension table for weekly calendar
[10 empty] | 6 | Dashboard | Power BI Dax Query | PLANT_WeeklyActualReturn | Summaryized Pallet_Return_Data by week and return to plant
[10 empty] | 7 | Dashboard | Power BI Dax Query | PLANT_WeeklyExpectedReturn | Summarize Simulation_Plant_Baseline Expected Return by week and return to plant
[10 empty] | 8 | Dashboard | Power BI Dax Query | WeeklyActualReturn | Summaryized Pallet_Return_Data by week without location
[10 empty] | 9 | Dashboard | Power BI Dax Query | WeeklyExpectedReturn | Summarize Simulation_Plant_Baseline Expected Return by week without location

## Data Flow
Data Flow:
SAP BW Data Pulls
3PL Actual Outbound Pallets Emails (CSVs)
Pallet Simulation Output (csv)
PowerBI Dashboard
Alteryx Shared Drive
Branch Location Mapping (Manual Excel File)
Power Automate Flow
Pallet Simulation Model (ipynb)
Pallet Simulation Assumptions
Actual Pallet Return Data (csv)
All recorded returns
Actual Outbound Pallet Data (csv)
Salinas, Richmond, Naperville, Chicago, Portland
Alteryx Data Transformation Flow
3PL Actual Outbound Pallets by Branch (csv)
3PL Actual Outbound Pallets to Customers (csv)
Alteryx Shared Drive
Alteryx Shared Drive

## Code & Resources
Links to Deliverables:
Links to Resources:
\\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets
Links to Code:
\\mznapwapalt002\alteryx\NA_BIS\Everything On Pallets\Code\turns_metric.ipynb

## Unit Test Checklist
Testing Checklist:
Data
Check input data matches expected output
Conduct back-end data check to ensure all required data for metric calculation is flowing in and makes sense
Data up to date/refreshed prior to UAT Kick-off
Data Flow diagram updated and ready to publish
Development
Product developed as per wireframe and aligned with stakeholders on differences
Migrated tool from Dev to Test environment
Filters/slicers work throughout all tables/visuals
Filters/slicers filter other filters
Filters, charts & tables do not contain empty or nulll values
Ensured all colors in charts/graphs are cohesive and easy to read
Saved the tool withouth filtering the front end
Checked front-end data results against business provided insights for accuracy check
Visuals filter each other according to business requirements
User Acceptance Testing (UAT)
Develop plan for UAT Feedback collection
Develop plan for UAT testing
Complete "UAT Scenarios" tab
Scheduled meeting to kick-off UAT

## UAT Scenarios
UAT Scenarios:
Task ID | Task Name | Description | Unit Tester | Unit Test Date | User Tester | User Test Date | Pass/Fail | Comments
1. Design
1.1 | Wireframe Layout | Does the tool look and feel close to what was agreed on?
1.2 | Dashboard Flow | Does the dashboard flow in a logical/intuitive way?
1.3 | Filters | Are all required filters present? Do they allow to get to the desired granularity?
1.4 | Date | Date filter is clearly defined both on how it operates as well as date type?
1.5 | Graph/Charts | Do colors and layout make sense? Any ambiguous charts that require explanation?
1.6 | Graph/Charts | Decimal points and labels are uniform throughout the report? Units are clearly stated?
2. Accuracy & Performance
2.1 | Metrics/KPIs Test | Do all metrics/KPIs make sense? Do they align with business SMEs expectations?
2.2 | YOY/Period comparison | Does all data compare to the correct period and is responsive to the Date filter?
2.3 | Refresh Cadance | Dashboard is refreshed for UAT at the agreed cadance?
2.4 | Speed | Is the dashboard quick to react to filters and other selections?
3. Project Specific Test cases (fill in for each project)
3.1 | Use this space to write relevant test cases for the project at hand